## PHP
PARC Report Gallery Application
Start Date:17-10-2012 |  | End Date: 20-11-2012 |  |  |  | Available Man Hours : 8 * 19 days = 152 Hrs
ID | Task | Expected Est Hrs | Actual Est Hrs | Developer | Start Date | Expected End Date | Actual End Date | Status | Comments
1 | Requirement study | 4 | 4 | Jayant | 17/10/2012 | 17/10/2012 | 17/10/2012 | Completed
2 | SRS document | 4 | 4 | " | 17/10/2012 | 17/10/2012 | 17/10/2012 | Completed
3 | Sketch - Screen Design | 4 | 8 | " | 25/10/2012 | 27/10/2012 | 27/10/2012 | Completed | Depands upon the approval of submited Requirement Study & SRS
4 | Database Design | 8 | 8 | " | 2012-01-11 | 2012-02-11 | 2012-02-11 | Completed | Fine Tunning in progress
5 | Site Diagram | 8 | 8 | " | 2012-02-11 | 2012-02-11 | 2012-02-11 | Completed
6 | Site Basic Framework in MVC | 16 | 16 | " | 2012-05-11 | 2012-06-11 | 2012-06-11 | Completed
User side
7.1 | Home page | 4 |  | " | 2012-07-11 | 2012-07-11 | 2012-07-11 | Completed
7.2 | Registration-User | 4 |  | " | 2012-08-11 | 2012-08-11 | 2012-08-11 | Completed
7.3 | Login & log out | 2 |  | " | 2012-08-11 | 2012-08-11 | 2012-08-11 | Completed
7.4 | Report Gallery - Home Page | 16 |  | " | 14/11/2012 | 15/11/2012 | 15/11/2012 | Completed
7.5 | Order Report | 4 |  | " | 16/11/2012 | 16/11/2012 | 16/11/2012 | Completed
7.6 | Advanced Search | 4 |  | " | 17/11/2012 | 17/11/2012 | 19/11/2012 | Completed
7.7 | Order Status | 4 |  | " | 18/11/2012 | 18/11/2012 | 19/11/2012 | Completed
7.8 | Suggestions & Complaints | 4 |  | " | 19/11/2012 | 19/11/2012 | 19/11/2012 | Completed
7.9 | Request for Special report | 4 |  | " | 19/11/2012 | 19/11/2012 | 19/11/2012 | Completed
Admin side
8.1 | Admin login & log out | 2 |  | " | 2012-08-11 | 2012-08-11 | 2012-08-11 | Completed
8.2 | User Management Console | 8 |  | " | 2012-09-11 | 2012-09-11 | 2012-10-11 | Completed
8.3 | Report Category Managment | 4 |  | " | 2012-09-11 | 2012-09-11 | 2012-10-11 | Completed
8.4 | Report Country Managment | 4 |  | " | 2012-09-11 | 2012-09-11 | 2012-10-11 | Completed
8.5 | Report Target User Managment | 4 |  | " | 2012-09-11 | 2012-09-11 | 2012-10-11 | Completed
8.6 | Order Status | 8 |  | " | 18/11/2012 | 18/11/2012 | 19/11/2012 | Completed
8.7 | Report Gallery update | 24 |  | " | 2012-11-11 | 13/11/2012 | 13/11/2012 | Completed